## Store Project Timeline
New Store: High Level Project Timeline
Example
|  | Start Date | Weeks before Completion | Expected Duration (days) | Completion Date | Complete?
Phase I : Feasibility
Market Feasibility
| Initial Market Study complete | 2017-01-01 |  | 30 | 2017-01-31
| Project Business Plan complete | 2019-04-01 |  | 30 | 2019-05-01
| Create 1st draft proforma | 2019-05-05 |  | 1 | 2019-05-06
| Update Market Study | 2019-07-01 |  | 31 | 2019-08-01
Site Securing and Feasibility
| Site selection criteria ready | 2017-01-01 |  | 30 | 2017-01-31
| Site(s) chosen for analysis/development | 2017-01-31 |  | 70 | 2017-04-11
| Preferred site identified | 2017-04-11 |  | 15 | 2017-04-26
| Sublease signed (with inspection period) | 2019-05-16 |  | 1 | 2019-05-17
| End of inspection period - payment due | 2019-06-17 |  | 0 | 2019-06-17
| Site visit on 6/10/19 | 2019-06-10 |  | 21 | 2019-07-01
| Initial Store Schematic Design and Site Feasibility | 2019-07-01 |  | 75 | 2019-09-14
Financial Feasibility
| Update project budget | 2019-09-01 |  | 7 | 2019-09-08
| Update proforma | 2019-09-08 |  | 10 | 2019-09-18
| Confirm budget is within financial constraints | 2019-09-18 |  | 1 | 2019-09-19
General Manager Recruitment
| GM Hired | 2019-06-17 |  | 116 | 2019-10-11
Phase IIa Preliminary Planning
Prelim Planning Kickoff
| New GM gets up to speed on progress to date | 2019-10-11 | ---- | 7 | 2019-10-18
| New GM confirms store design criteria, programming & schematic drawing | 2019-10-18 | ---- | 28 | 2019-11-15
| External support in place (Owners Rep, Architect, Refrigeration, GC, Int. Design) | 2019-11-15 | ---- | 120 | 2020-03-14
RFP & Hire Owners Rep
RFP & Hire Architect
RFP & Hire GC
RFP & Hire Interior Designer
Select Refrigeration Contractor
| Develop Scope of work & timeline for Prelim. Planning Phase with design team | 2020-03-14 |  | 0 | 2020-03-14
| Complete Fixture Plan Preliminary Design | 2020-02-01 |  | 30 | 2020-03-02
| Receive preliminary Equipment List with estimated costs | 2020-03-02 | ---- | 7 | 2020-03-09
| Receive preliminary construction estimates | 2020-03-02 | ---- | 7 | 2020-03-09
Prelim Design Complete
| Review project plans with city - approvals & variances determined | 2020-03-02 |  | 7 | 2020-03-09
| Update project budget | 2020-03-09 |  | 1 | 2020-03-10
Financing: Loan Term sheets Complete
| Financing stack (Senior, Junior, Member) commitments in place | 2020-02-01 |  | 38 | 2020-03-10
Real Estate
| Decide whether to extend current lease or negotiate new lease w/ contingencies | 2019-10-11 |  | 75 | 2019-12-25
Prelim. Design Pro Forma Complete
| Update proforma if needed based on cost estimates | 2020-03-10 |  | 0 | 2020-03-10
PHASE IIb - Project Development & Financing
Store Systems
| Develop organizational chart & begin system planning | 2020-03-17 |  | 60 | 2020-05-16
Design Development
| Decide on equipment procurement process/strategy/partners | 2020-03-09 | ---- | 21 | 2020-03-30
| Fixture Plan Design Development Complete | 2020-03-17 |  | 14 | 2020-03-31
| Receive projected Equipment Costs - based on real quotes | 2020-03-31 |  | 30 | 2020-04-30
| Develop preliminary merchandising plan | 2020-03-31 |  | 21 | 2020-04-21
| Architectural & Engineering Design Development | 2020-03-31 |  | 75 | 2020-06-14
| Interior Design Development | 2020-03-31 |  | 45 | 2020-05-15
| Selection of General Contractor if using Design-Bid process | 2020-06-14 |  | 24 | 2020-07-08
| Receive projected Construction Costs - based on real bids | 2020-07-08 |  | 7 | 2020-07-15
Financing Secured
| All sources of funds secured | 2020-03-31 |  | 91 | 2020-06-30
| Final update of Proforma | 2020-07-15 |  | 5 | 2020-07-20
Loan Closing
| Loan closing procedures | 2020-07-21 |  | 1 | 2020-07-22
PHASE III - Construction & Opening
| Building Permit - approval for all work | 2020-06-14 |  | 28 | 2020-07-12
| Determine store set up schedule | 2020-07-12 | ---- | 1 | 2020-07-13
| Update Project Timeline | 2020-07-13 | ---- | 1 | 2020-07-14
Equipment schedule complete
| Determine plan for monitoring construction & receiving equipment | 2020-07-13 |  | 1 | 2020-07-14
| All insurance certificates & permits in hand - ready for construction | 2020-07-14 |  | 4 | 2020-07-18
Store Construction Begins
| Start of Construction | 2020-07-18 | ---- | 4 | 2020-07-22
| Monitor Construction progress & costs | 2020-07-18 |  | 120 | 2020-11-15
Hiring Plan in Place
| Determine adjustments to staffing & timeline (if needed) | 2020-07-18 |  | 15 | 2020-08-02
| Order Equipment except which is needed onsite earlier | 2020-09-22 | 12 | 0 | 2020-09-22
| Refrigeration | 0
| Hoods and foodservice equipment | 0
| Custom fixtures | 0
| Electronics | 0
| General Store Equipment | 0
| Clarity with city process of CO/TCO & other permits that may affect opening | 2020-09-22 | 12 | 7 | 2020-09-29
Co-op Construction complete:TCO
| Ultility hookup dates secured | 2020-09-22 | 12 | 7 | 2020-09-29
Store programming & merchandising complete
| Store Set-up Planning complete | 2020-09-22 | 12 | 14 | 2020-10-06
| Monitor equipment delivery & installation | 2020-09-22 | 12 | 75 | 2020-12-06
| Recommend product line & pricing to 85% | 2020-09-22 | 12 | 30 | 2020-10-22
| Finalize product line & Pricing | 2020-10-06 | 10 | 30 | 2020-11-05
| Place inventory orders | 2020-10-20 | 8 | 45 | 2020-12-04
| Draft smallwares orders | 2020-09-22 | 12 | 45 | 2020-11-06
| Place smallwares orders | 2020-10-06 | 10 | 0 | 2020-10-06
New Staff Hiring complete
| Staff are hired and trained | 2020-11-03 | 1 | 35 | 2020-12-08
| Store Set-up - Phase I: Center store | 2020-11-17 | 4 | 14 | 2020-12-01
Equipment Installation
Prepare new spaces for operations and merchandising
Departmental sets
All products are in POS and have signs
| Store Set-up - Phase II -- Produce, Deli, Meat, Cheese | 2020-11-24 | 3 | 14 | 2020-12-08
Equipment Installation
Prepare new spaces for operations and merchandising
Departmental sets
Store Set
All products are in POS and have signs
| POS item file verification - handheld check | 2020-12-08 | 1 | 7 | 2020-12-15
| Final store cleanup | 2020-12-08 | 1 | 7 | 2020-12-15
| Project complete | 2020-12-15 |  | 0 | 2020-12-15
Opening
| Store opening | 2020-12-15 |  | 0 | 2020-12-15
Formulas:
Start Date = [Completion Date, row above]
Start Date = [Start Date, row above]
Completion Date = [Start Date]+[Expected Duration (days)]